## Sheet1
Legend: | Documentation: |  |  |  |  | Enhancement
Task: | Day:
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
Schedule tasks
Project planning
Front-end for different types of users
Move database connection logic from DBConnection into model classes
Servlets to delegate viewer functions, and login with httpsession
Admin - Delete user
General - Sign up as a new patient
Admin - Add new patient, nurse, doctor
Admin - Edit User (change password, etc…)
Admin - List all patients (Choose between NHS & Private patients)
Doctor & Nurse - Forward a patient
Calendar API for booking timetabling system
Map API for lookup addresses, linked to booking
Admin - Change price of appointments
Booking system update
Map API for lookup addresses, linked to booking
Admin - List all invoices in time period (from X to Y)
Doctor & Nurse - Issue prescription to patient
Patient - Re-request repeat prescriptions
Admin - Remove patient from schedule
Patient - Cancel their appointments
Patient - Book an appointment
Doctor & Nurse - Book an appointment
Admin - View schedule of GP within two given dates
Doctor & Nurse - View own schedule
Admin - Get private payments for X time (daily, weekly, monthly)
Admin - Get NHS payments for X time (daily, weekly, monthly)
Admin - Create turnover for X time (daily, weekly, monthly)
Patients - Pay their bills (only in full), if they are a private patient
Doctor & Nurse - Issue invoice to patient
Gantt Chart