## Sheet1
Legend: | Documentation: |  |  |  |  | Enhancement
Task: | Day:
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
Schedule Tasks
Initial project plan with Gantt chart
Mock validate payment methods
Calendar API for booking/timetabling system
Clean up Date/Time data types
Add table validation to prevent duplicates
Secure session, including timeout, using cookies
Front end design
Viewer classes created
User filtering
Extra: Approval of patient signup
Extra: Password Security
Extra: Heat map of client location
Task delivery form, progres slides and presentation