## Sheet1
Task Delivery Form - Sprint 3:
Project title: | ESD Assignment | [5 empty] | Group: | 3
Module leader: | Mehmet Aydin | [5 empty] | Date: | 2020-01-21
| Tasks: | [29 empty] | Signatures
Group Members: | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
Austin Harper | X | X | X | [9 empty] | X |  | X | [9 empty] | X | X
Conran Pearce | X | X |  | X |  |  | X | X | X | [13 empty] | X |  |  |  |  | X
Harrison Bennion | X | X | [7 empty] | X | X | [6 empty] | X |  |  |  |  | X | X
Morgan Welch | X | X |  | X | X | X |  |  | X |  |  | X |  |  |  | X |  |  | X | X | X | X
Sam Kirk | X | X | [11 empty] | X |  |  | X | [9 empty] | X
Status of Completion (%) | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100 | 100
Task Number: | List of Tasks:
1 | Schedule tasks
2 | Project planning
3 | Patient - Let patient pay bill in full
4 | Patient - Issue a prescription
5 | Patient - Request a repeated prescription
6 | Patient - Book an appointment with a selected doctor or nurse
7 | Patient - Cancel own appointment
8 | Patient - View referral details attached to self
9 | Doctor & Nurse - Issue a prescription
10 | Doctor & Nurse - Display own schedule for today
11 | Doctor & Nurse - Forward a patient to a hospital or clinic
12 | Doctor & Nurse - Book an appointment for themselves and select a patient
13 | Doctor & Nurse - Create invoice following an appointment
14 | Admin - Change the prices per service or period of consulatation
15 | Admin - List all invoices in selected period
16 | Admin - Add doctor or nurse
17 | Admin - Remove patient from surgery
18 | Admin - Approval of Patient Sign-up
19 | Doctor, Nurse & Admin - Add a patient
20 | Doctor, Nurse & Admin - List all patients page
21 | Doctor, Nurse & Admin - List NHS patients
22 | Doctor, Nurse & Admin, List private patients
23 | Patient, Doctor, Nurse & Admin - Be able to view schedule
24 | Calendar API for booking/timetabling system
25 | Filters for User Permissions/Authentication
26 | Extra - Button to display turnover/invoices for today, this week and month
27 | Extra - Admin editing user so that we can change between an employee and a client
28 | Extra - Password security