## Sheet1
Legend: | Documentation: |  |  |  |  | Enhancement
Task: | Day:
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
Schedule Tasks
Initial project plan with Gantt chart
Provided Database to be connected
Basic Login Front-end
Login permission handling
Task delivery form and progress slides
+